## Summary
Feature Story Test Loop Tracker | Near My Route
Run date | 2026-07-04
Branch | codex/feature-story-test-loop
Source of truth inspected | AGENTS.md, README.md, CONTEXT.md, src/app, src/components, src/lib, scripts, unit tests, focused e2e scripts
Total stories | 29
tested-pass | 29
tested-fail | 0
partial | 0
blocked | 0
fixed-retest-pass | 0
Defects opened this run | 0
Defects fixed this run | 0
Residual risk | No real post-redesign Van Packet dogfood notes were supplied in this loop; validated coverage uses synthetic/demo data only.

## Stories
story id | feature area | role | story | preconditions | expected behavior | failure state | reversal or exit behavior | source evidence | test method | status | defect id | fix commit or file reference | retest evidence | residual risk
NMR-STORY-001 | App shell and navigation | Field SLP | As a field SLP, I can move between Route, Facilities, Import Schedule, and Outreach on desktop and mobile. | App loaded with demo state. | Top-level tabs/buttons switch the visible workflow without losing persisted route state. | Wrong tab content, hidden workflow, or route state lost. | User can return to Route from any top-level tab. | src/components/NearMyRouteApp.tsx tabs; README What is included | npm run screenshots:walkthrough -- --no-archive; npm run test:e2e:dogfood | tested-pass |  | No code fix needed | Screenshots plus dogfood route script exercise mobile nav and route return. | None
NMR-STORY-002 | App shell and navigation | Developer/demo user | As a tester, I can reset the demo state to known defaults. | LocalStorage may contain prior state. | Reset restores mock facilities, route stops, outreach logs, dogfood checklist, and sample import text. | Stale local data remains or PHI-like dogfood notes persist. | User can continue from the reset default state. | src/components/NearMyRouteApp.tsx resetDemo; src/lib/storage.ts | npm test; npm run screenshots:walkthrough -- --no-archive | tested-pass |  | No code fix needed | Unit storage migration tests and screenshot workflow clear LocalStorage before demo state. | None
NMR-STORY-003 | Route planning | Field SLP | As a field SLP, I can see route readiness, the best add-on, route stops, and map context on the Route screen. | Demo/current route is loaded. | Readiness summary, candidate hierarchy, route list, and map render without blocking primary actions. | Best add-on is missing, layout hides actions, or route readiness is unclear. | User can inspect facilities or import a route from the route screen. | README; NearMyRouteApp desktop/mobile route panels; RouteMap.tsx | npm run screenshots:walkthrough -- --no-archive; npm run test:e2e:dogfood | tested-pass |  | No code fix needed | Visual walkthrough covers home route dashboard and confirmed route/map states. | None
NMR-STORY-004 | Route planning | Field SLP | As a field SLP, I can filter add-on candidates by detour, follow-up age, known contacts, and same-day friendliness. | Confirmed route exists and candidates are available. | Filters change candidate eligibility and show an empty state when nothing matches. | Filtered candidates ignore guardrails or empty state is unclear. | User can relax filters to see candidates again. | src/lib/routeCalculations.ts; src/components/NearMyRouteApp.tsx filters | npm test; npm run screenshots:walkthrough -- --no-archive | tested-pass |  | No code fix needed | Route calculation unit tests cover detour/contact/recent/same-day filtering; screenshots include no-match state. | None
NMR-STORY-005 | Route planning | Field SLP | As a field SLP, I can open a preview route with a selected add-on inserted at the best route position. | A route-aware opportunity exists. | Preview handoff builds a Google Maps directions URL with the candidate inserted at the calculated position. | Preview route is unordered or opens without the candidate. | No app state is permanently changed by previewing. | src/lib/googleMaps.ts; src/lib/routeCalculations.ts; NearMyRouteApp previewRouteWithAddOn | npm test; npm run screenshots:walkthrough -- --no-archive | tested-pass |  | No code fix needed | Unit tests cover insertion/URL helpers; walkthrough covers possible add-on state. | None
NMR-STORY-006 | Route planning | Field SLP | As a field SLP, I can add a possible add-on tentatively and remove it if plans change. | Candidate has an add-on opportunity. | App inserts a tentative route stop, logs added_to_route, shows confirmation, and can remove the stop. | Route stop remains stuck or added status is inconsistent with route state. | Remove tentative stop reverses the route addition. | NearMyRouteApp addTentatively/removeTentativeStop; src/lib/todayStatus.ts | npm run test:e2e:dogfood; npm test | tested-pass |  | No code fix needed | Dogfood script adds/removes Encompass and verifies LocalStorage state; unit tests cover added status derivation. | None
NMR-STORY-007 | Route planning | Field SLP | As a field SLP, I can open the current confirmed route in Google Maps only when route locations are trusted. | Current route has confirmed locations, or has unconfirmed imported/private stops. | Confirmed routes open a Google Maps directions URL; unconfirmed routes show a disabled Confirm locations for Maps action. | Maps opens with unconfirmed/fallback coordinates. | Confirming locations re-enables Maps handoff. | src/lib/googleMaps.ts; src/lib/locationTrust.ts; NearMyRouteApp currentRouteLocationWarning | npm run test:e2e:location-confirmation; npm run test:e2e:van-packet; npm test | tested-pass |  | No code fix needed | Browser scripts verify blocked/unblocked Maps handoff and generated URL shape. | None
NMR-STORY-008 | Route planning | Field SLP | As a field SLP, I can export the current route summary as a CSV. | Current route exists in LocalStorage. | Export downloads a dated CSV with sequence, facility, address, schedule, studies, route status, outreach status, and added drive minutes. | CSV is missing headers or route rows. | Export has no state mutation; user remains on route screen. | NearMyRouteApp exportRouteSummary | Targeted Playwright one-off export validation; npm run build | tested-pass |  | No code fix needed | One-off browser validation checked filename, CSV headers, and Memorial SNF row. | None
NMR-STORY-009 | Facilities | Field SLP | As a field SLP, I can search and filter Facilities, then open a facility detail/review view. | Facility master data is loaded. | Search narrows facilities and Review fit opens detail with contact, notes, route fit, and status actions. | Facility cannot be found or detail opens stale data. | Back action returns to prior workflow. | README Facilities; NearMyRouteApp Facilities tab and DetailDrawer | npm run test:e2e:dogfood; npm run screenshots:walkthrough -- --no-archive | tested-pass |  | No code fix needed | Dogfood script searches Northwest and opens Review fit; screenshots include facility detail possible add-on state. | None
NMR-STORY-010 | Facilities | Field SLP | As a field SLP, I can edit contacts, add a contact, choose preferred method, and mark the recommended Primary SLP Contact. | Facility detail or outreach contact setup is open. | Contact edits persist, only one recommended contact remains primary, and text readiness follows preferredMethod=text plus dialable phone. | Wrong contact becomes primary or call-preferred contacts make texting ready. | User can change preferred method or recommended contact again. | src/lib/format.ts; NearMyRouteApp ContactSetupPanel | npm run test:e2e:contacts; npm test | tested-pass |  | No code fix needed | Contact e2e verifies adding Ken/Nora, preferred method changes, primary swap, and readiness. | None
NMR-STORY-011 | Facilities | Field SLP | As a field SLP, I can choose among multiple text-ready SLP Contacts before starting a message. | Facility has multiple text-preferred dialable contacts and no single recommended contact. | App shows Choose text contact and logs the chosen contact after explicit Mark texted. | Wrong contact is used or chooser is bypassed incorrectly. | User can close chooser or choose a different contact on next attempt. | NearMyRouteApp TextContactPicker/startTextFlow | Targeted Playwright one-off multi-contact chooser validation | tested-pass |  | No code fix needed | One-off browser validation seeded Lisa and Ken, selected Ken, and verified Ken in outreach log. | None
NMR-STORY-012 | Outreach | Field SLP | As a field SLP, I can copy/use the approved PHI-safe Outreach Message. | Facility-level outreach action is available. | Only the approved facility-level template is copied or displayed. | Message includes patient/clinical details or unapproved wording. | User must explicitly mark texted after sending. | src/lib/format.ts OUTREACH_MESSAGE; README Outreach lifecycle | npm test; npm run test:e2e:messages; npm run test:e2e:dogfood | tested-pass |  | No code fix needed | Unit and browser tests verify exact approved message and explicit confirmation. | None
NMR-STORY-013 | Outreach | Field SLP | As a field SLP, placeholder or invalid phone numbers never enable Messages handoff or Texted today logging. | Facility has no phone, 555 phone, or invalid text. | Text action is disabled or asks for real phone; no texted log is written. | Placeholder data counts as outreach or opens Messages. | User can enter a real dialable phone to proceed. | src/lib/format.ts phone helpers; ContactSetupPanel | npm test; npm run test:e2e:messages; npm run test:e2e:outreach-priority | tested-pass |  | No code fix needed | Tests cover 555, invalid values, no phone, edit-to-real-phone, and no premature Mark texted. | None
NMR-STORY-014 | Outreach | Field SLP | As a field SLP, Messages handoff behaves correctly on desktop and mobile. | Text-ready contact exists. | Desktop copies template and shows fallback instructions; mobile attempts sms handoff; neither logs texted until Mark texted. | Texted today is logged on open/copy instead of explicit confirmation. | Mark texted records the selected contact and status. | NearMyRouteApp openMessagesForContact/markTexted | npm run test:e2e:messages; npm run test:e2e:dogfood | tested-pass |  | No code fix needed | Browser scripts verify desktop fallback, mobile sms attempt path, clipboard content, and explicit texted logging. | None
NMR-STORY-015 | Outreach | Field SLP | As a field SLP, I can triage the Outreach queue by Text First, ready-to-text, needs-phone, and response queues. | Route and facilities are loaded. | Best route-useful not-contacted candidate is highlighted and current-route facilities/private stops are excluded. | Queue promotes wrong facility or includes route-only/private stops. | Changing status/contact info recalculates queues. | src/lib/outreachPriority.ts; NearMyRouteApp Outreach tab | npm test; npm run test:e2e:outreach-priority; npm run test:e2e:van-packet | tested-pass |  | No code fix needed | Unit tests and e2e verify Text First priority, unconfirmed route block, and private stop exclusion. | None
NMR-STORY-016 | Outreach | Field SLP | As a field SLP, I can log waiting, no patients today, possible add-on, do-not-contact, added, and clear do-not-contact states. | Facility is visible in detail or queue. | Today Status reflects latest log plus route stop truth; do-not-contact persists until cleared. | Status conflicts with route state or cannot be reversed. | Clear do-not-contact reactivates facility; removing add-on reverses added route state. | src/lib/todayStatus.ts; NearMyRouteApp logOutreach/removeTodayAddOn | npm test; npm run test:e2e:dogfood; npm run test:e2e:outreach-priority | tested-pass |  | No code fix needed | Unit tests cover status derivation and clear behavior; dogfood validates possible add-on and clear do-not-contact. | None
NMR-STORY-017 | Schedule import | Field SLP | As a field SLP, I can paste a simple schedule and review matched existing Facility stops. | Import Schedule tab is open with facility-level route text. | Parser extracts times, names, addresses, study counts, auto-matches strong existing facilities, and clears expanded controls on reparse. | Known facility creates duplicates or controls remain stale. | User can confirm matched stops into tomorrow route. | src/lib/scheduleImport.ts; NearMyRouteApp import flow | npm test; npm run test:e2e:import; npm run test:e2e:dogfood | tested-pass |  | No code fix needed | Browser import happy path confirms 3 existing stops without duplicate facilities. | None
NMR-STORY-018 | Schedule import | Field SLP | As a field SLP, uncertain import rows must be resolved before Confirm route is enabled. | Import review includes weak match, placeholder, blank, or unresolved action. | Confirm button is disabled with clear row blocking reason until use existing, create new, private stop, or skip is selected. | Unresolved row creates a Facility/route stop. | User can skip or resolve row and then confirm. | src/lib/scheduleImport.ts importRowBlockingReason | npm test; npm run test:e2e:import | tested-pass |  | No code fix needed | Unit and browser tests cover unresolved, unselected, placeholder create-new, and skip behavior. | None
NMR-STORY-019 | Schedule import | Field SLP | As a field SLP, I can create a new Facility from an import row, but it requires Location Review before ranking/Maps. | Review row is explicitly set to Create new facility with real name/address. | New Facility is stored once with locationStatus=needs_confirmation and route uses that stop. | New facility is trusted immediately with fallback coordinates. | Location confirmation is required before add-on ranking and app-generated Maps. | src/lib/scheduleImport.ts; src/lib/locationTrust.ts | npm test; npm run test:e2e:import; npm run test:e2e:location-confirmation | tested-pass |  | No code fix needed | Tests verify create-new guardrails and unconfirmed location blocking. | None
NMR-STORY-020 | Import review UI | Field SLP | As a field SLP, matched import rows collapse to reduce review work and can be expanded with keyboard or click. | Strong matched rows are visible in mobile and desktop review. | Collapsed row hides low-priority controls; Change match toggles controls and aria-expanded state. | Reviewer must scan unnecessary controls or keyboard toggle fails. | Reparse collapses rows again. | NearMyRouteApp ImportMatchedSummary/ImportReviewCards/table | npm run test:e2e:import | tested-pass |  | No code fix needed | Import e2e validates mobile and desktop collapse behavior, keyboard Enter, and reparse reset. | None
NMR-STORY-021 | Van Packet import | Field SLP | As a field SLP, I can paste a Van Packet email body/map link and optional PDF table text, then parse safe route review rows. | Van Packet mode is selected. | Parser extracts van name, map stops, start/end skips, private stop hints, safe notes, and scrolls/focuses review. | Raw packet text remains visible or unsafe fields appear. | Reviewer resolves rows like schedule import rows. | src/lib/vanPacketImport.ts; NearMyRouteApp Van Packet UI | npm test; npm run test:e2e:van-packet; npm run screenshots:walkthrough -- --no-archive | tested-pass |  | No code fix needed | Van Packet e2e verifies sample parse, summary, scroll, and cleared paste inputs. | None
NMR-STORY-022 | Van Packet import | Field SLP | As a field SLP, private/home-health Van Packet stops stay route-only and never become Facilities or outreach candidates. | PDF/map stop suggests a private route stop. | Review row becomes Private route stop; route stop stores privateLocation; Facilities and Outreach exclude it. | Private address becomes a Facility/contact candidate. | Private stop can be confirmed for route geometry only. | src/lib/vanPacketImport.ts; src/lib/routeLocations.ts; NearMyRouteApp private route stop flow | npm test; npm run test:e2e:van-packet; npm run screenshots:walkthrough -- --no-archive | tested-pass |  | No code fix needed | Browser test confirms Private route stop 3 is not in Facilities/Outreach and only participates after location confirmation. | None
NMR-STORY-023 | Van Packet import | Field SLP | As a field SLP, useful safe PDF facility labels can be remembered as local aliases only after manual match. | Review row has safe alias candidate and selected existing Facility. | Remember alias checkbox adds safe alias; alias-only future matches remain in review unless address also supports them. | Unsafe/private/contact labels are saved as aliases or random alias auto-matches. | User can leave alias unchecked. | src/lib/facilityAliases.ts; src/lib/vanPacketImport.ts; src/lib/scheduleImport.ts | npm test; npm run test:e2e:van-packet | tested-pass |  | No code fix needed | Unit tests cover alias safety; Van Packet e2e verifies WESTCHASE OUTPOST manual learning and future review state. | None
NMR-STORY-024 | Van Packet import | Field SLP | As a field SLP, route start/end anchors and original map links are preserved without becoming Facility work. | Van Packet map link includes meet/return and route stops. | Start/end anchors are skipped from review, sourceMapLink is preserved on route stops, and original map link can open separately. | Meet point becomes an outreach candidate or source map is lost. | User can open original source map separately from app-generated Maps. | src/lib/vanPacketImport.ts; NearMyRouteApp vanPacketSummary/currentRouteSourceMapLink | npm run test:e2e:van-packet; npm run screenshots:walkthrough -- --no-archive | tested-pass |  | No code fix needed | Van Packet e2e checks route start/end skipped, sourceMapLink on stops, and original map link button. | None
NMR-STORY-025 | Location review | Field SLP | As a field SLP, I can confirm imported or private stop locations with real coordinates and clear route blocking. | Route contains unconfirmed imported/private location. | Location Review shows address lookup, coordinate inputs, validation errors, URL coordinate extraction, and Confirm Location. | Invalid/fallback/search-only coordinates are accepted. | Confirmed location removes route warning and re-enables ranking/Maps. | src/lib/locationTrust.ts; src/lib/googleMaps.ts; LocationConfirmationCard | npm test; npm run test:e2e:location-confirmation; npm run test:e2e:van-packet | tested-pass |  | No code fix needed | Browser scripts verify invalid latitude, fallback guard, search URL warning, !3d/!4d parsing, and unblock. | None
NMR-STORY-026 | Dogfood workflow | Field SLP | As a field SLP, I can use the one-route dogfood checklist and notes to capture workflow friction safely. | Demo tools/dogfood checklist is open. | Checklist items persist, safe workflow notes persist, PHI-looking notes are rejected and legacy unsafe notes are cleared on hydration. | Patient or clinical details persist in LocalStorage. | User can edit notes after removing unsafe content. | src/lib/privacy.ts; NearMyRouteApp DogfoodChecklist/storage hydration | npm test; npm run test:e2e:dogfood | tested-pass |  | No code fix needed | Unit privacy tests and dogfood browser script verify safe note persistence, PHI warning, and legacy cleanup. | None
NMR-STORY-027 | Persistence | Field SLP | As a returning local user, my route, contacts, outreach logs, dogfood notes, aliases, and location state persist locally. | LocalStorage key near-my-route-state-v1 exists. | State rehydrates and migrations preserve old data while marking fallback/unknown locations for confirmation. | Reload loses workflow state or trusts stale fallback locations. | Reset demo intentionally clears local working state. | src/lib/storage.ts; NearMyRouteApp hydration effect | npm test; npm run test:e2e:dogfood; npm run test:e2e:contacts | tested-pass |  | No code fix needed | Storage unit tests cover migration; e2e reload checks route/log/contact/dogfood persistence. | None
NMR-STORY-028 | Visual QA | Designer/reviewer | As a reviewer, I can generate PHI-safe screenshots for the key workflow states. | Developer runs screenshot walkthrough. | Script starts local app or uses SCREENSHOT_BASE_URL, clears LocalStorage, captures desktop/mobile states, writes manifest, and uses synthetic data only. | Screenshots include unsafe data or miss key states. | Latest output can be regenerated; archive optional. | scripts/capture-walkthrough-screenshots.ts; docs/SCREENSHOT_WALKTHROUGH.md | npm run screenshots:walkthrough -- --no-archive | tested-pass |  | No code fix needed | Screenshot command passed and refreshed output/screenshots/latest with manifest. | None
NMR-STORY-029 | Build/runtime | Developer | As a developer, I can build the current Next.js app without type or route errors. | Dependencies installed; Next 16.2.9 project. | next build compiles, runs TypeScript, and prerenders / and /_not-found. | Build or app route fails. | No runtime state mutation. | package.json; src/app/page.tsx; src/app/layout.tsx | npm run lint; npm run build | tested-pass |  | No code fix needed | Lint and production build passed after story verification. | None

## Validation
Command | Result | Evidence
npm run screenshots:walkthrough -- --no-archive | passed | Wrote output/screenshots/latest
npm test | passed | 63 tests passed
npm run test:e2e:import | passed | Import guardrails browser validation passed
npm run test:e2e:messages | passed | Open Messages fallback browser validation passed
npm run test:e2e:outreach-priority | passed | Outreach priority browser validation passed
npm run test:e2e:dogfood | passed | Dogfood route browser validation passed
npm run test:e2e:contacts | passed | Contact setup browser validation passed
npm run test:e2e:location-confirmation | passed | Location confirmation browser validation passed
npm run test:e2e:van-packet | passed | Van packet import browser validation passed
Targeted Playwright one-off: route CSV export and multi-contact chooser | passed | Validated CSV filename/header/row and Ken chooser/logging
npm run lint | passed | eslint completed
npm run build | passed | Next.js 16.2.9 production build completed

## Defects
defect id | story id | severity | reproduction | observed | expected | status | fix | retest evidence
none |  |  | No story failures found during this loop. |  |  | closed-no-defect |  | All listed validation commands passed.

## Non User Facing
Inventory item | Source evidence | Reason no user story was created | Verification/status
API endpoints | rg --files src/app; no route handlers under app/api | No implemented API surface in this local-first prototype. | Documented as not user-facing.
Authenticated pages | README and src/app route tree | No auth implemented or requested; app is local-first. | Documented as not user-facing.
Server actions/jobs/migrations | Repo file inventory | No backend jobs, server actions, migrations, Supabase, or database code exists. | Documented as not user-facing.
Notifications and Settings icon buttons | NearMyRouteApp shell buttons only | Shell controls are decorative placeholders with no implemented behavior; no feature claim in README. | Tracked as non-story residual shell risk.
Static public SVG assets | public/*.svg | Framework starter assets not exposed as distinct workflow behavior. | Documented as not user-facing.